## Short Project Description
Short description
Aims to develop a solution for remotely accessing and controlling doors. Involves a front-end and back-end application.
Overall required capabilities
Login system, Door Unlock/Lock capability, security aspect
Context Description
Software engineering project, to experience real devellopement oraganisation

## ProductBacklog
US Nr. | Theme | User Stories |  |  | Acceptance Criteria | Blockers / Dependencies | Story | Status | Priority | Sprint | US accepted | MoSCoW
1 | Preparation | Developer | perform a technological assessment | we can investigate and select the needed technologies to develop the system | _ each component has a techonology defined for its implementation _ techologies integration are assessed and understood |  | 5 | 3 | 1000 | 0 | 14.10.23 done done | Must
2 | Preparation | Developer | Define functionalites | we can define the different functionalities of the project | we have a list of functionalites accepted by dev and PO |  | 5 | 3 | 990 | 0 | 18.12.2023 done done | Must
3 | Preparation | Developer | Version control and developpment environment setup | library setup, git setup | we all have the same working environement |  | 10 | 3 | 980 | 1 | 8.1.2024 done done | Must
4 | Design | Developer | Front-end mockup | We want to define the layout and connection of the app | We have an interface that satisfies the functions | 2 | 20 | 3 | 970 | 1 | 8.1.2024 done done | Must
5 | Design | PO | Front-end mockup validation | The PO can see the design | The PO validates the mockup | 4 | 1 | 3 | 960 | 1 | 8.1.2024 done done | Must
6 | Design | Developer | Back-end pipeline | We want to define the pipeline for the back-end to achieve the identified functionalities | We have a plan for the developers |  | 15 | 3 | 970 | 1 | 8.1.2024 done done | Must
7 | Development | Developer | Front-end development | We want to develop the front-end | The mockup is realised |  | 50 | 3 | 950 | 1,2,3 | 20.1.2024 done | Must
8 | Development | Developer | Back-end development | We want to develop the back-end | The back-end is realised |  | 50 | 3 | 950 | 1,2,3 | 20.1.2024 done | Must
9 | Integration | Developer | Integrate front and back together | We want to have a working app | The app is working | 7,8 | 35 | 3 | 940 | 3 | 2024-01-20 | Must
10 | Presentation | Developer | Prepare the presentation | We need to prepare the presentation | we know what we want to talk about on the presentation day | 9 | 10 | 3 | 930 | 3 | 2024-01-21 | Must
11 | Documentation | User | Create the user guide | Create a guide that will allow the user to use the app flawlessly | The guide is finish and covers all the functionnalites availables | 9 | 5 | 3 | 920 | 3 | 2024-01-21 | Must
12 | Project delivery | Developer | Delivers the project | Deliver the project (package presentation, code, documentation, presentation) | All documents and code are delivered | 11 10 | 3 | 3 | 910 | 3 | 2024-01-26 | Must
13
14
[13 empty] | 0 | initial state
[13 empty] | 1 | rejected
[13 empty] | 2 | selected
[13 empty] | 3 | done
0
Totaux
[7 empty] | Total SP |  | 11470
[7 empty] | Total rejected SP |  | 0
[7 empty] | Total without rejected SP |  | 11470
Note on I1: ====== ID#AAAAIvwmHCk Author (2020-10-03 08:55:52) Enter 1, 2 or 3 and the satus is automaticaly displayed (blue = todo, yellow = in progress, green = done and accepted, red= rejected) The task is considered as 'done':3 when all points decided in team are solved (example of done definition : documentation in code, unittests passed, functional tests passed, user manual completed, …)

## Feuil1
Requirements: | Name | Detail
| Login | Users must be able to log in on the website with a username and a password
| Lock/unlock doors | Users must be able to see a list of the doors they have access to and lock/unlock them
| Notifications for user | Users would be able to subscribe to notifications for one or more doors, and get notified on door status change
| User creation deletion | Admin user must be able to create or delete "simple" users
| Access door-user | Admin must be able to assign door access to simple users
| lock/unlock all doors | Admin should be able to lock/unlock all doors
| realtime feedback on doors | Users must be able to see if the door is locked/unlocked in real time
| logs of door access | There should be a log for each door with infos about when they were closed/opened and by who
| history of registered doors | Users should be able to access the logs of their doors, with infos about when they closed/opened them
| Security | passwords must be stored as hash in DB

## Release Roadmap - Velocity
Informations collected during the sprint review
Sprints
| 0 | 1 | 2 | 3
SP done per sprint |  | 46 | 29 | 55
Average
Todo |  | 46 | 29 | 55
Rejected
Done (cumulative)
Product Backlog growing
Sprints
| 0 | 1 | 2 | 3
Total SP at beginning of sprint
Nbr SP selected for sprint
Changed est.
New Stories
Total SP at end of sprint
Scope Change

## Sprint 0
|  |  | Sprint | 0
0 |  |  | Start date
1
2 |  |  | End date (included)
3 |  |  | Initial sprint estimation (SP)
4
6 |  |  | Sprint goal
5 |  |  | Nbr working days
7
9
8
ID US.task | Task Name | Resp. | Initial Estimate |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
0.1
0.2
0.3
1.1
2.0
2.1
3.0
4.0
6.0
5.0
7.0
9.0
9.1
8.0
|  | Total | 0
|  | Remaining | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Therical | 0 |  | 0 | 0 | 0 | 0 | 0
Impediments
[8 empty] | Impediments | Status
Note on D15: ====== ID#AAAAIvwmHCs Author (2020-10-03 08:55:52) This is the team's initial assessment of how much work is needed to implement this task. The unit is hours. This part must be filled by developers only. Not by the product owner
Note on D31: ====== ID#AAAAIvwmHC0 Author (2020-10-03 08:55:52) Initial total of Scrum units

## Sprint 1
|  |  | Sprint | 1
|  |  | Start date | 2023-12-18
|  |  | End date (included) | 2024-01-08
Initial sprint estimation (SP)
|  |  | Sprint goal | 2024-01-07
|  |  | Nbr working days | 5
ID US.task | Task Name | Resp. | Initial Estimate |  | Day 1 | Day 2 | Day 3 | Day 4
3.1 | Environment setup | Martin | 10
4.1 | Front-end mockup | Guillaume, Noah | 20
6.1 | Backend pipeline | Marco, Martin | 15
5.1 | Mockup validation | Martin, Marco, Noah, Guillaume | 1
|  | Total | 46
|  | Remaining | 46 |  | 0 | 0 | 0 | 0
|  | Therical | 46 |  | 46 | 34.5 | 23 | 11.5
Impediments
[8 empty] | Impediments | Status
Note on D11: ====== ID#AAAAIvwmHCs Author (2020-10-03 08:55:52) This is the team's initial assessment of how much work is needed to implement this task. The unit is hours. This part must be filled by developers only. Not by the product owner
Note on D23: ====== ID#AAAAIvwmHC0 Author (2020-10-03 08:55:52) Initial total of Scrum units

## Sprint 2
|  |  | Sprint | 2
|  |  | Start date | 2024-01-08
|  |  | End date (included) | 2024-01-15
|  |  | Initial sprint estimation (SP) | 5-7 days
|  |  | Sprint goal | 2024-01-12
|  |  | Nbr working days | 5 | we will try our best not to work on the weekend
ID US.task | Task Name | Resp. | Initial Estimate |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
7.1 | Login form | Noah | 3
7.2 | Dashboard | Noah | 5
7.3 | Door edition page | Noah | 5
8.1 | Database creation | Guillaume | 1
8.2 | Prisma setup (Databse to backend relation) | Guillaume | 3
8.3 | Web server setup | Martin, Marco | 2
8.4 | Login system implementation | Guillaume, Martin | 5
8.5 | Dashboard | Martin | 5
|  | Total | 29
|  | Remaining | 29 |  | 0 | 0 | 0 | 0 | 0
|  | Therical | 29 |  | 29 | 21.75 | 14.5 | 7.25 | 0
Impediments
[8 empty] | Impediments | Status
Note on D13: ====== ID#AAAAIvwmHCs Author (2020-10-03 08:55:52) This is the team's initial assessment of how much work is needed to implement this task. The unit is hours. This part must be filled by developers only. Not by the product owner
Note on D35: ====== ID#AAAAIvwmHC0 Author (2020-10-03 08:55:52) Initial total of Scrum units

## Sprint 3
|  |  | Sprint | 3
|  |  | Start date | 15.01.24
|  |  | End date (included) | 22.01.24
|  |  | Initial sprint estimation (SP) | 5-7 days
|  |  | Sprint goal | 2024-01-12
|  |  | Nbr working days | 5 | we will try our best not to work on the weekend
ID US.task | Task Name | Resp. | Initial Estimate |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
7.1 | Login form | Noah Pencherek | 5
8.1 | Creation of all the methods needed for the different queries | Guillaume Bessard | 30
8.2 | Prisma setup (Databse to backend relation) | Guillaume Bessard | 10
10.1 | Start of the presentation | Guillaume Bessard | 1
10.2 | Preparation of the presentation | All | 9
|  | Total | 55
|  | Remaining | 55 |  | 0 | 0 | 0 | 0 | 0
|  | Therical | 55 |  | 55 | 41.25 | 27.5 | 13.75 | 0
Impediments
[8 empty] | Impediments | Status
Note on D13: ====== ID#AAAAIvwmHCs Author (2020-10-03 08:55:52) This is the team's initial assessment of how much work is needed to implement this task. The unit is hours. This part must be filled by developers only. Not by the product owner
Note on D35: ====== ID#AAAAIvwmHC0 Author (2020-10-03 08:55:52) Initial total of Scrum units

## Retrospective
SPRINT 0
End : 14.10.2023
Name | What went Good ? | What went Wrong ? | How to improve ? | General feedback / Sprint Review
SPRINT 1
End : 08.01.2024
Name | What went Good ? | What went Wrong ? | How to improve ? | General feedback / Sprint Review
Marco | Good engagement when under pressure of time | Hard to plan when vacation happens | Communication to avoid wasting time | Good
Martin | Tasks division and execution | Time management in general, will be improved | Better planning and keep with deadline | Other project on the line and we suceeded anyway to keep deadline
Guillaume | Start of prisma was successful | Time Mangement x2 | Better planning and keep with deadline | same
Noah | Mock up realisation | Some details to correct | Correct point and we good | Good project, niceeeee
SPRINT 2
End : 15.01.2024
Name | What went Good ? | What went Wrong ? | How to improve ? | General feedback / Sprint Review
Guillaume | Check username/password went perfectly | Stuck with Prisma on request with join to get user with access to a specific door | Try to search more in Prisma doc to find the solution | Sickness is bad :(
Martin | Sprint was succesful. Back end developement is going strong | Problems with launching project on Marco's computer | Keep in mind from the start that project will be launched on differents computers | Good
Noah | Front end is ready for review | Problems with doing the dropdown integrated in the lists of locations | - | Nice autonomy !
Marco | Back end functionality are working | Environment for code developing keeps on giving several compatibility problems | Fresh start of the environment | Learning new things is cool
SPRINT 3
End : 21.01.2024
Name | What went Good ? | What went Wrong ? | How to improve ? | General feedback / Sprint Review
Guillaume | Tasks are done | Prisma keeps on giving problems. Still searching for solutions. | Searching, docs, and asking forums | Try hard
Martin | Back-end is done finally | Nothing to announce | Presenting this in the lessons learned slide | Good experience
Noah | Front-end is working fantastically | Early setup but in the end everything works fine | Learning for next occasion | Mission accomplished
Marco | Back-end is done finally. Presentation is ready | Nothing to announce | Presenting this in the lessons learned slide | We did it

## Done Definition
DONE DEFINITION FOR ALL USER STORIES

## Journal
Date | Who | What | Time | Type | Colonne1

## DailyMeeting
Who | Sprint | When | The 3 questions : What did you do since last time? / What will you work on today? / Do you have any obstacles? |  |  | Impediments
(Example) Due to Google Sheet bug with image, please use https://steven95968.invisionapp.com/freehand/Daily-meeting-notes-Qd6cJQ7aq to show our daily meeting notes
|  |  | What did you do since last time | What will you work on today | Do you have any obstacles?